## Sheet1
CIT Test - 08 Oct 19
No | Module | Function | Issue Description | Front End | Backend | Update from Developer
1 | Dashboard | View Details | POD and DO images is not display properly, the same POD images showing | TBA, no api
2 | Dashboard | View Details | Receiver Address please allign left | fixed
3 | Dashboard | View Details | Copy, CSV, Excel, Print function no response | TBA
4 | Dashboard | View Details | Consignment under New status not displaying | already called the api, should be no issue from front end
5 | Shipment | Shipment Listing | There are no options to view consignment details | TBA, please provide wireframe, from listing and also the details, and also api
6 | Shipment | Shipment Listing | Packaging Type not displaying correctly
7 | Shipment | Shipment Listing | Wrong "status" detected - Awaiting dropoff?
8 | Shipment | Create Shipment | Delivery Service showing description instead of Service Name? E.g. Premium become "this is premium service…." | fixed
9 | Shipment | Create Shipment | Requested Pickup date by default is blank | fixed
10 | Shipment | Create Shipment | Packaging Type only showing Parcel (Document missing)
11 | Shipment | Create Shipment | Goods Description always showing error of "Description is required" after add goods | it is design in that way, no issue
12 | Shipment | Create Shipment | Unable to confirm shipment, showing disabled | fixed
13 | Shipment | Create Shipment | Unable to Print shipment | TBA
14 | Shipment | Create multiple Shipment | Unable to import shipment, showing upload shipment failed | fixed
15
Please provide me wireframe update for any changes on the UI side
and also the supporting api, or else I won't know which api to use